NICVD HOSPITAL KARACHI

AI WAITING ROOM MANAGER

9-Step Patient Journey

FULL-FLEDGED INSTALLATION & IMPLEMENTATION PLAN A practical 30-week blueprint for reducing OPD waiting time, improving patient flow, and deploying safe, on-premise AI across NICVD Karachi.

Prepared for: NICVD Director, IT Leadership, Clinical Operations, Quality & Patient Services

Prepared by: Senior Healthcare AI Implementation Consultant

Version: 1.0  |  Date: 23 September 2026

Scope: OPD, Emergency coordination, patient navigation, queue prediction, follow-up support

# Document Control & Executive Summary

| Control Item | Detail |
| --- | --- |
| Document owner | NICVD Digital Health / Project Management Office |
| Primary audience | NICVD Director, IT team, clinical leadership, operations, security and quality teams |
| Implementation horizon | 30 weeks, approximately 7 months |
| Recommended package | Standard Full Campus, PKR 2.35 Crore, excluding taxes and civil works |
| Go-live approach | One-OPD beta, then controlled campus rollout |
| Safety boundary | AI supports routing, prediction, communication and follow-up; clinicians retain diagnosis and treatment authority |

## Executive Summary

NICVD provides approximately 1.4 million episodes of free cardiac care annually, with around 2,500 OPD and 1,200 Emergency patients each day. Current waiting times of 65-115 minutes create avoidable congestion, uncertainty, repeated manual coordination and high pressure on clinical and front-desk teams. The AI Waiting Room Manager is designed to move patients through a clear, multilingual, measurable journey while preserving human clinical judgement.

The solution combines self-service kiosks, Urdu/English language processing, queue prediction, smart allocation, LED and SMS guidance, follow-up automation, and on-premise integration with hospital systems. The key automation is Smart Queue Allocation: the system assigns patients to the appropriate queue and service lane using rules plus predictive scoring, replacing repetitive manual sorting and coordination estimated at 125 staff-hours per day.

Implementation principle Automate coordination, not clinical judgement. No AI component in this plan diagnoses, prescribes, or overrides a doctor.

## Success Definition

Reduce patient waiting time toward the target band of 16-40 minutes.

Achieve at least 50% wait reduction in the beta OPD against a two-week baseline.

Reach at least 80% waiting-time prediction accuracy and 99% display uptime.

Provide a safe fallback through local cache, manual tokens, UPS and documented downtime procedures.

Create an auditable, maintainable platform that NICVD staff can operate after handover.

# SECTION 1 | OBJECTIVE AND PROBLEM STATEMENT

NICVD’s daily patient volume is exceptional for a cardiac-care institution. High throughput, complex routing, emergency prioritization, limited visibility into queue status and repeated manual handoffs combine to produce long and variable waits. Patients may not know where to go next, front-desk teams repeatedly answer the same questions, and supervisors lack a single real-time view of demand versus capacity.

## Why AI is Needed

| Problem | Operational impact | AI-enabled response |
| --- | --- | --- |
| Unpredictable arrival surges | Queues become overloaded before capacity is visible | Forecast demand and continuously recalculate waiting time |
| Manual patient sorting | Staff spend time reading, classifying and directing patients | NLP-assisted intake plus rules-based queue allocation |
| Low patient visibility | Patients crowd counters or miss their turn | LED/SMS guidance and multilingual status updates |
| Distributed information | HIS, EMR, LIS and front desk may not share context | FHIR gateway with auditable event exchange |
| Follow-up leakage | Patients leave without clear next step | Automated reminders and follow-up task creation |

## Daily Process Workflow: AS-IS to TO-BE

| Step | AS-IS challenge | TO-BE process with AI integration |
| --- | --- | --- |
| 1. Arrival | Patient joins a counter queue with limited guidance | Kiosk or assisted desk check-in; language and accessibility options |
| 2. Intake | Staff manually capture and interpret basic information | AI collects structured responses and supports Urdu/English NLP |
| 3. Estimate | Waiting time is based on experience or static tokens | Model predicts wait using queue, service rate, priority and historical patterns |
| 4. Allocate | Staff manually direct patient to a lane | AI assigns queue/lane automatically, with human override |
| 5. Navigate | Patient searches for area or repeatedly asks staff | LED, printed token, SMS and verbal guidance |
| 6. Consult | Doctor evaluates patient clinically | Doctor remains fully responsible for diagnosis and treatment |
| 7. Disposition | Referral/follow-up steps may be inconsistent | AI prepares reminders and creates follow-up prompts for staff |
| 8. Exit | Patient leaves with variable instructions | Discharge summary, next-step confirmation and feedback capture |

PRIMARY AUTOMATION Step 4: Smart Queue Allocation. This is the single most important manual-work reduction: automated routing can remove repetitive sorting and coordination estimated at 125 hours of staff effort daily, while preserving override and escalation controls.

# SECTION 2 | SDLC FOR THE NICVD PROJECT

The software development life cycle is adapted for a live hospital environment. Each phase has an explicit clinical, operational, technical and governance output. Workstreams overlap deliberately so that security, integration and patient safety are designed in rather than inspected at the end.

| Phase | NICVD application | Timing | Primary outputs |
| --- | --- | --- | --- |
| 1. Planning | Confirm sponsor, scope, budget, success measures, governance and pilot OPD | W1-W2 | Project charter, RACI, risk register, measurement plan |
| 2. Analysis | Map AS-IS/TO-BE workflows, integrations, teams, data, safety and accessibility needs | W2-W5 | Signed requirements, interface inventory, workflow maps, case-study insights |
| 3. Design | Design service blueprint, UX, architecture, data model, security, fallback and reporting | W4-W8 | Approved solution design, prototypes, threat model, test strategy |
| 4. Development | Build kiosk, queue engine, AI services, dashboards, integrations and device management | W7-W15 | Feature-complete release candidate, interface adapters, deployment package |
| 5. Testing | Validate clinical safety, workflows, integrations, performance, security, accessibility and resilience | W18-W23 | Test evidence, resolved defects, UAT and go-live recommendation |
| 6. Deployment / Maintenance | Install, train, pilot, hypercare, handover and ongoing AMC | W24-W30 | Pilot results, operating model, runbooks, handover and maintenance plan |

## Phase 1: Planning, W1-W2

Appoint executive sponsor, project manager and clinical safety lead.

Confirm pilot OPD, operating hours, patient-volume assumptions and baseline measurement method.

Agree decision rights: clinical safety, data protection, architecture, change control and incident escalation.

Define target outcomes, including wait reduction, prediction accuracy, uptime, patient satisfaction and safety incidents.

## Phase 2: Analysis, W2-W5

Analysis must be performed on the floor, not only in meeting rooms. Observe arrival peaks, registration, triage, consultation, diagnostics, pharmacy/referral and discharge. Measure queue length, service time, rework, staff touchpoints, exceptions and accessibility barriers.

| Analysis stream | Questions to answer | NICVD deliverable |
| --- | --- | --- |
| Workflow mapping | Where do patients wait, backtrack, or get redirected? | AS-IS and TO-BE swimlanes with exception paths |
| Integration needs | Which HIS/EMR/LIS, registration, SMS and reporting interfaces exist? | Interface catalogue, owners, data dictionary and FHIR mapping |
| Teamwork analysis | Who makes decisions, who overrides, who supports patients? | RACI, shift model, escalation and training needs |
| Safety and privacy | What is the minimum data, consent, retention and audit requirement? | Hazard log, privacy controls and clinical safety cases |

## Short Real-World Case Study and Implications

A NICVD operating day with 1,976 patients demonstrates the scale problem: even a 20-second manual intervention per patient can consume roughly 11 staff-hours, before counting repeated questions, queue corrections, missed calls or escalation. The implication is not to remove people; it is to reserve people for exceptions, reassurance, triage and clinical work. AI should classify routine flow, predict congestion, expose anomalies and prompt action earlier.

Use historical arrival and service data to forecast demand by hour and clinic.

Create priority rules that are transparent, testable and approved by clinical operations.

Monitor override rate as a safety and trust signal, not as a failure metric.

Use a human-in-the-loop model for ambiguous language, incomplete information and emergency escalation.

# SDLC CONTINUED | DESIGN, DEVELOPMENT, TESTING AND DEPLOYMENT

## Phase 3: Design, W4-W8

Design a patient journey that works for elderly patients, low-literacy users, Urdu speakers and assisted check-in.

Define architecture: on-premise application services, secure API gateway, device management, queue engine, model services, audit logging and reporting.

Prototype kiosk screens, LED content, SMS templates, staff dashboard and manual override workflows.

Complete threat modelling, role-based access, encryption, retention, backup, disaster recovery and downtime design.

Secure Design Approval at W8 before production build proceeds.

## Phase 4: Development, W7-W15

Build React kiosk, queue management services, prediction service, multilingual NLP intake, staff dashboard and reporting.

Implement HL7 FHIR API gateway and adapters to available HIS/EMR/LIS capabilities.

Configure token, queue, priority, appointment, referral and follow-up rules.

Build model monitoring, audit logs, feature flags, configuration management and rollback.

Enroll test devices in MDM and package kiosk lockdown, remote support and update controls.

## Phase 5: Testing, W18-W23

Execute functional, integration, performance, security, accessibility and resilience testing.

Test a representative 2,500-patient OPD load, plus emergency-priority scenarios and degraded dependencies.

Run clinician-led safety review: no diagnostic output, no autonomous treatment decision, clear escalation.

Complete UAT with front desk, nurses, doctors, IT, security, quality and patient-service representatives.

Reach Security Readiness W19 and Go-Live approval W23.

## Phase 6: Deployment / Maintenance, W24-W30

Install and commission pilot devices, run baseline comparison, then operate one OPD beta at 500 patients/day.

Provide floor walkers, 24/7 hypercare for the first 30 days, and daily incident review.

Complete Pilot Exit W26 after meeting agreed criteria.

Roll out to remaining locations, complete documentation, train support teams and hand over at W30.

GOVERNANCE GATE No gate is a calendar formality. Each gate requires evidence, named approvers, open-risk disposition and a clear go/no-go decision.

# SECTION 3 | 30-WEEK SCHEDULE, DURATIONS AND TIMELINE

The following schedule is the baseline delivery plan. Activities overlap where practical, but gates are fixed control points. Weeks are counted from project kickoff.

| Phase | Activity | Start-End Week | Deliverable | Gate Approval |
| --- | --- | --- | --- | --- |
| Planning | Charter, governance, pilot selection, baseline design | W1-W2 | Approved charter, RACI, risk register |  |
| Analysis | Floor observation, AS-IS/TO-BE, data and integration discovery | W2-W5 | Requirements pack, workflow maps, interface inventory | Requirements sign-off W5 |
| Design | UX prototypes, architecture, safety, security, fallback and reporting | W4-W8 | Solution design, threat model, prototype, test strategy | Design Approval W8 |
| Development | Kiosk, queue engine, NLP, prediction, dashboard, API gateway | W7-W15 | Feature-complete release candidate |  |
| Environment readiness | Servers, VLAN, Wi-Fi, MDM, test data, monitoring | W14-W19 | Validated environment, device baseline, security evidence | Security Readiness W19 |
| System and UAT testing | Functional, integration, performance, security, accessibility, resilience | W18-W23 | Test report, defect closure, UAT sign-off | Go-Live W23 |
| Pilot deployment | One OPD, 500 patients/day, baseline comparison, hypercare | W24-W26 | Pilot report, KPI dashboard, exit recommendation | Pilot Exit W26 |
| Campus rollout and handover | Remaining devices, training, runbooks, AMC, governance | W27-W30 | Operational acceptance, handover pack, support model | Handover W30 |

## Gantt View

| Planning | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Analysis |  | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Design |  |  |  | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Development |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Environment readiness |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ | ■ | ■ |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Pilot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Rollout/Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ■ | ■ | ■ | ■ |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

Weeks: W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30

Critical path: requirements sign-off → design approval → security readiness → go-live → pilot exit → handover. Any slippage at a gate must be handled through formal change control, not silent compression of testing.

# SECTION 4 | TEAM MEMBERS, STAKEHOLDERS AND JOB DESCRIPTIONS

NICVD should nominate accountable counterparts before W2. Vendor and NICVD roles must be paired so knowledge transfer starts on day one.

| Role | Job Description / Role Responsibility | NICVD Counterpart |
| --- | --- | --- |
| Executive Sponsor | Owns strategic outcome, budget, cross-department decisions and gate approvals. | NICVD Director / delegated executive |
| Project Manager | Owns plan, RAID log, dependencies, meetings, reporting, acceptance and change control. | PMO / IT project manager |
| Clinical Safety Lead | Approves clinical workflow, priority rules, escalation, safety cases and no-diagnosis boundary. | Senior cardiologist / clinical governance nominee |
| Solution Architect | Owns end-to-end architecture, on-premise deployment, non-functional requirements and technical decisions. | Head of IT / enterprise architect |
| AI/NLP Lead | Owns Urdu/English NLP, prediction models, evaluation, drift monitoring and explainability. | NICVD data/analytics nominee |
| HIS Integration Expert | Maps HL7/FHIR, registration, EMR, LIS, SMS and reporting interfaces; manages test data. | HIS/EMR integration lead |
| Hardware & Device Manager | Owns survey, kiosk/LED/tablet/server inventory, MDM, spares, installation and swap process. | Biomedical / IT infrastructure manager |
| Data Protection/Security Lead | Owns privacy, RBAC, encryption, logging, vulnerability management, incident response and retention. | Information security / compliance lead |
| QA Lead | Owns test strategy, traceability, defect triage, UAT evidence and release recommendation. | Quality assurance manager |
| Training & Change Manager | Owns role-based training, floor support, communications, adoption metrics and handover readiness. | HR/training and patient services lead |

## Stakeholder Operating Rhythm

| Cadence | Participants | Purpose |
| --- | --- | --- |
| Daily during installation/pilot | PM, floor support, IT, patient services, vendor lead | Incidents, queue performance, device status and blockers |
| Weekly delivery review | All workstream leads | Plan, RAID, gate evidence, decisions and change requests |
| Clinical safety review | Clinical safety lead, doctors, nursing, QA, AI lead | Priority rules, overrides, incidents, false positives and escalation |
| Monthly steering committee | Executive sponsor, PM, IT, clinical and finance leads | Budget, benefits, risks, scope and gate readiness |

# SECTION 5 | COST ESTIMATION IN PKR

The estimates below are implementation planning figures for decision-making. Final pricing depends on site survey, taxes, civil works, existing infrastructure, integration complexity and procurement terms.

| Package | Scope | Estimated Cost | Best fit |
| --- | --- | --- | --- |
| Basic Pilot | 1 OPD; limited kiosks, displays and integration; suitable for proof of value | PKR 95 Lakh | Single-department pilot |
| Standard Full Campus (Recommended) | Campus deployment with 10 kiosks, 15 LED displays, 30 tablets, 2 servers, software, integration, training and maintenance | PKR 2.35 Crore | NICVD OPD plus coordinated campus flow |
| Premium Enterprise | Expanded redundancy, advanced analytics, broader integrations, extended support and enterprise controls | PKR 4.2 Crore | Multi-site or enterprise-grade expansion |

## Standard Full Campus Breakdown

| Cost component | Included scope | Estimate |
| --- | --- | --- |
| Hardware | 10 kiosks, 15 LED displays, 30 tablets, 2 rack servers | PKR 1.25 Crore |
| Software | Queue manager, kiosk application, NLP, prediction, dashboard, monitoring | PKR 65 Lakh |
| Integration | HL7 FHIR API gateway, HIS/EMR/LIS adapters, SMS/reporting interfaces | PKR 25 Lakh |
| Training / Maintenance | Training, documentation, initial maintenance and rollout support | PKR 20 Lakh |
| Total | Standard Full Campus | PKR 2.35 Crore |

Commercial assumptions Recurring support after Year 1: PKR 35,000 per month. Estimates exclude taxes, civil works, major electrical remediation, building-wide cabling upgrades and third-party SMS charges.

## Cost Control Recommendations

Approve the Standard package only after confirming server-room readiness and existing HIS integration capabilities.

Use the Basic package only as a controlled learning pilot, not as the final target architecture.

Ring-fence patient-safety, cybersecurity and resilience spend; these are not optional add-ons.

Track benefits using the same baseline and KPI definitions used for the beta exit decision.

# SECTION 6 | INSTALLATION SETUPS

## Site Survey and Physical Design

The survey team must walk the complete patient journey during peak and off-peak periods. Record power points, network drops, sunlight/glare, queue geometry, wheelchair access, acoustic conditions, visibility of LED displays, staff sightlines and safe cable routes.

| Setup area | Requirement | Acceptance check |
| --- | --- | --- |
| Network | Dedicated VLANs for kiosks, displays, tablets, servers and management; Wi-Fi 6 where wireless is used; QoS for operational traffic | VLAN segmentation tested, coverage survey passed, monitored bandwidth |
| Server room | 2 rack servers, UPS, network switch, environmental monitoring, secure rack and restricted access | Redundancy, backup, UPS runtime and recovery test documented |
| Kiosks | 10 locations: main OPD entrance, registration, cardiology OPD zones, diagnostics interface, pharmacy/referral, emergency coordination and high-volume waiting areas | Accessible height, privacy screen, printer/token option, visible help point |
| LED mounts | 15 displays at decision points, waiting areas and corridor junctions | Visibility, power, mounting safety, content legibility and zone mapping |
| Tablets | 30 managed devices for staff/volunteers, triage support and floor navigation | MDM enrolled, locked configuration, charging and spare allocation |
| MDM | Enrollment, kiosk lockdown, remote health, patching, certificate rotation and inventory | 100% of deployed devices report healthy and assigned owner/location |

## Eight-Step Installation Process

Approve site survey and mark final device locations.

Prepare civil, power, network, VLAN and Wi-Fi changes.

Rack servers, UPS, firewall rules, backups and monitoring.

Install and label kiosks, LED displays, tablets and accessories.

Enroll devices in MDM, apply locked profiles, certificates and remote support.

Deploy application, configuration, queue zones, templates and integration endpoints.

Run commissioning tests: power, network, display, token, SMS, audit, fallback and recovery.

Complete floor training, pilot readiness review and signed installation acceptance.

## Failure Fallback and Downtime Mode

Local cache keeps the latest queue configuration, patient token state and safe operating messages available during temporary network loss.

Manual tokens and paper queue sheets remain available at each staffed entry point.

When integration is unavailable, staff use a controlled downtime form and reconcile events after recovery.

UPS supports controlled operation and graceful shutdown; a documented UPS drill is required before pilot.

Critical alarms, queue congestion and clinical escalation remain human-owned at all times.

# SECTION 7 | TECHNICAL DETAILS OF THE 9-STEP PATIENT JOURNEY

The table below defines the intended operating contract between AI, people and hospital systems. Timing is indicative and should be recalibrated during the two-week baseline and pilot.

| Step | Time | AI role | Human role | Output |
| --- | --- | --- | --- | --- |
| 1. Arrival & Check-in | 2-5 min | Kiosk captures identity/visit context, language and accessibility preference; validates against registration where available. | Front desk or volunteer assists, verifies exceptions and emergency escalation. | Patient token, visit record, language and queue request |
| 2. AI Collects & Analyzes Data | 1-2 min | Urdu/English NLP interprets structured and guided responses; flags incomplete or ambiguous inputs. | Staff handle low-confidence, hearing/language or safeguarding cases. | Normalized intake, confidence score, exception flag |
| 3. Predicts Waiting Time | 1-2 min | Predicts wait using queue length, service rates, clinic, priority, time of day and historical patterns. | Supervisor reviews anomalies and capacity constraints. | Patient-facing wait estimate and internal forecast |
| 4. Smart Queue Allocation | 1 min | Rules plus predictive scoring automatically assign the best queue/lane and priority class; records rationale. | Authorized staff can override, document reason and escalate urgent cases. | Queue assignment, token, routing event and audit record |
| 5. Directed to Waiting Area | 2-10 min | Triggers LED zone, optional SMS, printed instruction and multilingual guidance. | Floor staff help patients navigate and address accessibility needs. | Confirmed location/zone and current queue status |
| 6. Consultation | 10-20 min | AI may surface administrative context or workflow prompts only; it must not diagnose. | Doctor performs history, examination, diagnosis and treatment decisions. | Clinical note and clinician-owned decision |
| 7. Treatment / Referral | 10-60 min | Coordinates next administrative step, referral queue, diagnostics or pharmacy workflow. | Clinician and staff approve treatment/referral and explain instructions. | Order/referral/treatment pathway and next action |
| 8. AI Manages Follow-up | 1-3 min | Creates reminders, follow-up prompts and patient communication schedule from approved care plan. | Care team confirms content, timing and channel; handles exceptions. | Follow-up task, reminder and escalation rule |
| 9. Discharged | 2-5 min | Confirms journey completion, captures feedback and closes queue events. | Staff provide discharge instructions and verify patient understanding. | Discharge confirmation, feedback and analytics event |

## Technical Stack and Controls

| Layer | Technology / control |
| --- | --- |
| Integration | HL7 FHIR API gateway; adapters for HIS/EMR/LIS, registration, SMS and reporting |
| AI/NLP | Python services; BERT-family NLP for Urdu/English; confidence thresholds and human fallback |
| Prediction | XGBoost-based waiting-time model with monitoring, calibration and drift alerts |
| Experience | React kiosk, staff tablet interface, LED display controller and responsive dashboard |
| Security | TLS 1.2+ in transit, AES-256 at rest, RBAC, audit trails, secrets management and least privilege |
| Deployment | On-premise servers with segmented VLANs, backups, UPS, monitoring and controlled updates |
| Safety | No autonomous diagnosis or treatment; override, escalation, auditability and clinical sign-off |

# SECTION 8 | BETA VERSION TESTING AND EVALUATION

The beta will run in one OPD during W24-W26, handling approximately 500 patients per day. A two-week baseline must be completed before the beta so results compare like with like: same OPD, comparable days, operating hours and measurement definitions.

## Pilot Design

| Element | Plan |
| --- | --- |
| Pilot location | One selected OPD with stable leadership, representative volume and measurable patient journey |
| Baseline | Two weeks of current-state observation and time stamps before enabling AI routing |
| Beta window | W24-W26, with staged activation and 30-day hypercare beginning at pilot go-live |
| Volume | Approximately 500 patients/day; include peak, off-peak, elderly, low-literacy and Urdu-speaking cohorts |
| Controls | Manual override, incident escalation, offline mode, daily review and rollback configuration |
| Evidence | Dashboard exports, sampled observation, patient survey, staff feedback, incident and override logs |

## Evaluation Metrics and Targets

| Metric | Target / interpretation | Measurement source |
| --- | --- | --- |
| Wait reduction | At least 50% versus two-week baseline | Token and service timestamps |
| Prediction accuracy | At least 80% within agreed tolerance band | Predicted versus actual wait |
| Display uptime | At least 99% during operating hours | Monitoring and device health logs |
| Override rate | Track by reason; investigate spikes, do not optimize blindly | Audit trail and supervisor review |
| Patient satisfaction | Increase by at least 20% versus baseline | Short multilingual survey |
| Safety incidents | Zero preventable safety incidents attributable to the system | Incident reporting and clinical review |
| Adoption | Staff use intended workflow; no unsafe shadow process | Observation, training checks and support tickets |

## Pilot Exit Criteria

All mandatory target metrics met or an approved remediation plan exists with named owner and date.

No unresolved high-severity safety, security or data-integrity defects.

UAT evidence signed by clinical, IT, quality and patient-service representatives.

Staff can operate queue overrides, downtime mode, device restart, escalation and incident logging.

Patient and staff feedback incorporated into rollout configuration.

Pilot report approved at Pilot Exit W26.

# SECTION 9 | QUALITY ASSURANCE

Quality assurance must demonstrate that the solution is safe, usable, reliable, secure and fit for the actual NICVD environment. Test evidence should be traceable from requirement to scenario, result, defect and closure.

| Test type | NICVD focus | Minimum evidence |
| --- | --- | --- |
| Functional | Check-in, token, intake, prediction display, allocation, override, navigation, follow-up and discharge | Test cases, expected results, execution record |
| Integration | HIS/EMR/LIS, registration, identity, appointments, referrals, SMS and reporting | Interface test pack, message logs, reconciliation report |
| Performance | 2,500 OPD load, peak arrivals, concurrent kiosk/tablet/display activity and degraded dependencies | Load profile, response times, capacity and tuning record |
| Security | Penetration test, RBAC, encryption, secrets, patching, logging, backup and incident response | Security test report, remediation evidence, approval |
| Accessibility | Elderly users, low-literacy users, Urdu, contrast, touch targets, assisted mode and privacy | Accessibility checklist, moderated user test, fixes |
| Resilience | UPS drill, server restart, network loss, local cache, manual tokens, backup restore and recovery | Resilience script, recovery times, signed drill result |

## Required QA Artifacts

Requirements traceability matrix linking each requirement to design, test and approval.

Approved test plan, test cases, test data and environment record.

Defect log with severity, owner, workaround, target fix and closure evidence.

Security assessment, penetration-test report and risk acceptance where applicable.

Clinical safety case, hazard log, override analysis and incident escalation procedure.

User acceptance test sign-off from clinical, operations, IT, security and quality.

Go-live checklist, rollback plan, monitoring dashboard and support contacts.

## Release Quality Rules

Release rule No go-live with an unresolved critical defect, an untested downtime path, missing audit trail, failed backup restore, or unclear clinical ownership of a patient-safety decision.

# SECTION 10 | MAINTENANCE, SUPPORT AND OPERATING MODEL

## Annual Maintenance Contract (AMC)

| Area | Operating commitment |
| --- | --- |
| Preventive maintenance | Quarterly preventive maintenance for kiosks, LEDs, tablets, servers, UPS, network and MDM configuration |
| Hardware replacement | 24-48 hour kiosk swap target; maintain a 5% spare pool for critical devices and accessories |
| Model operations | Monitor prediction accuracy, confidence, drift, data quality and override patterns; retrain only through controlled change |
| Application operations | Patch, vulnerability management, certificate rotation, backup verification, log review and release management |
| Service levels | Severity-based response, escalation and communications; report monthly on incidents, uptime and backlog |
| Governance | Monthly service review, quarterly clinical safety review and annual disaster-recovery exercise |

## Support Tiers

| Tier | Owner | Examples |
| --- | --- | --- |
| L1 | NICVD helpdesk / patient-services support | Basic device restart, token issue, user guidance, known-issue workaround |
| L2 | Vendor support | Application defect, integration issue, kiosk swap, model service issue, configuration correction |
| L3 | Solution architect / specialist team | Architecture failure, major security incident, complex model or integration decision |

## Hypercare and Steady State

First 30 days after pilot and campus rollout: 24/7 hypercare with floor coverage, daily stand-up, incident review and rapid configuration changes.

After hypercare: on-call support, scheduled maintenance windows, monthly KPI review and quarterly preventive maintenance.

Maintain a live runbook covering startup/shutdown, queue override, manual tokens, offline mode, UPS drill, restore, escalation and contacts.

Review model drift monthly and after material workflow, capacity or patient-population changes.

## Handover Pack at W30

As-built architecture, device inventory, network/VLAN map and server configuration.

Admin, support and user guides; training attendance and competency records.

Source/configuration baseline, model card, evaluation results and monitoring thresholds.

Integration catalogue, data dictionary, security evidence, backup/restore evidence and incident playbook.

Open-risk register, AMC contacts, spare-pool record, warranty details and improvement backlog.

# APPENDIX A | IMPLEMENTATION CHECKLIST

| Checkpoint | Owner | Evidence | Status |
| --- | --- | --- | --- |
| Project charter and sponsor confirmed | Executive Sponsor / PM | Signed charter and RACI | Open |
| Pilot OPD and baseline method confirmed | PM / Clinical Lead | Pilot charter and measurement plan | Open |
| AS-IS/TO-BE workflow approved | Operations / Clinical | Workflow maps and exception paths | Open |
| HIS/EMR/LIS interface catalogue complete | Integration Lead | Interface inventory and data dictionary | Open |
| Design, safety and security controls approved | Architecture / Security / Clinical | Design pack, threat model, safety case | Open |
| Test environment and devices ready | IT / Device Manager | Commissioning checklist | Open |
| Security readiness complete | Security Lead | Pen test and remediation evidence | Open |
| UAT and go-live decision complete | QA / Clinical / IT | UAT sign-off and go-live checklist | Open |
| Pilot exit approved | Steering Committee | Pilot KPI and incident report | Open |
| Handover accepted | NICVD IT / PMO | Runbooks, training and AMC acceptance | Open |

# APPENDIX B | KEY RISKS AND MITIGATIONS

| Risk | Impact | Mitigation / trigger |
| --- | --- | --- |
| Poor source data or missing integration | Wrong routing or duplicate work | Data profiling, reconciliation, manual fallback and staged interface activation |
| AI misclassification | Patient delay or unsafe priority | Confidence thresholds, human review, transparent rules and override audit |
| Low adoption | Shadow queues and inconsistent experience | Floor champions, role-based training, feedback loop and supervisor dashboard |
| Network/power interruption | Service disruption | VLAN monitoring, Wi-Fi survey, UPS, local cache, manual tokens and drills |
| Security/privacy incident | Patient harm, regulatory and reputational exposure | RBAC, encryption, logging, pen test, least privilege and incident playbook |
| Model drift | Reduced prediction accuracy | Monthly monitoring, threshold alerts, retraining governance and rollback |
| Procurement/civil delay | Schedule slippage | Early survey, long-lead inventory, alternate locations and gate-based replanning |

# APPENDIX C | APPROVAL RECORD

| Approval gate | Required approvers | Date / signature |
| --- | --- | --- |
| Requirements sign-off W5 | Executive Sponsor, PM, Clinical Safety Lead, IT Lead | ____________________________ |
| Design Approval W8 | Solution Architect, Security Lead, Clinical Safety Lead | ____________________________ |
| Security Readiness W19 | Security Lead, IT Lead, QA Lead | ____________________________ |
| Go-Live W23 | Executive Sponsor, Clinical Safety Lead, PM, QA Lead | ____________________________ |
| Pilot Exit W26 | Steering Committee and pilot leadership | ____________________________ |
| Handover W30 | NICVD IT, Operations, Vendor PM, Executive Sponsor | ____________________________ |

End of document. This installation plan is intended to be baselined at project kickoff and updated through controlled change management.